## Slide 1
Making the change sustainable
Lens | What changes | What we will do | How we measure it
PEOPLE HR / L&D + Ops leads | 75% of roles need reshaping in 2–3 years [4] 63% of rollout problems are human, not technical [5] | Role redesign per slide 1, with career paths ≥5 h AI training + coaching per person [2] | % staff using AI for ≥30% of daily tasks Quarterly trust / sentiment pulse
PROCESS Use-case owners + AI CoE | Value needs workflow redesign, not AI bolted on — only 21% have done it [3] NTI at 145 days is our bottleneck | Every use case ships with a redesigned SOP (agent step, human step, exception path) NTI reform: pre-approved patterns for reused agents; fewer, bigger use cases [1] | % live use cases with redesigned SOP NTI cycle time: 145 → <60 days
IT & TECHNOLOGY Platform team | Technology is the "20" in 10-20-70 [1] One delivery path replaces BU-bespoke builds | Single platform path from FY26; 8-week release cadence [7] Token metering from FY27 | Agents reused by ≥2 BUs (today: 0) Use cases in production (today 15 of 37)
RISK R&C + AI risk partner | 30% of gen-AI projects abandoned after PoC [6] Senior oversight of AI governance is the factor most tied to impact [3] | Risk partner in every pod; RCSA updated for agents (next slide) Named executive owner for AI governance | PoC → production conversion rate Override-rate and drift KRIs in threshold
Phase | People | Process | IT | Risk
FY25–26 ASSIST | AI literacy for all ops staff; use-case owners nominated | NTI quick fixes: forms, tracker, edit-after-submit | Platform MVP; metering design | Ops monitoring protocol; override-rate KRI (0–90 day plan)
FY26–28 ORCHESTRATE | First agent-manager roles; FDE per BU pod; role redesign published | Redesigned SOPs mandatory; pre-approved NTI patterns | Marketplace live; 8-week cadence; token quotas | Embedded risk partner; RCSA v2 with agent inventory
FY28–30 AUTONOMIZE | Hybrid teams managed by outcomes | Exception-only human workflows | Multi-agent orchestration; shared cache | Guardian agents; continuous assurance
References
[1] BCG, Closing the AI impact gap (AI Radar), Jan 2025
[2] BCG, AI at Work: momentum builds, but gaps remain, Jun 2025
[3] McKinsey, The state of AI, Mar 2025
[4] McKinsey, AI is everywhere; the agentic organization isn't yet, Apr 2026
[5] Prosci, Keys to unlocking AI adoption (n=1,107), May 2026
[6] Gartner, 30% of gen-AI projects abandoned after PoC, Jul 2024
[7] AI News, JPMorgan LLM Suite rollout, Dec 2025
OPEN POINTS (1) Nomura targets for each KPI (e.g. % staff trained by FY27; NTI <60 days). (2) Executive owner of AI governance to be named. (3) HR / L&D co-ownership of the People lens. (4) Redeployment-vs-reduction position per BU.
Notes: The technology on the previous slides is the easy part. BCG's finding across AI leaders is that they spend 10% of the effort on algorithms, 20% on data and technology and 70% on people, process and culture. Our plan is weighted the same way, across four lenses. People: 75% of roles need reshaping in the next two to three years, and 63% of rollout problems are human rather than technical - so we redesign roles with career paths, not just training, and give every person at least five hours of AI training with coaching, the threshold BCG links to sustained use. Measured by the share of staff using AI for a third or more of daily tasks and a quarterly trust pulse. Process: value comes from redesigning the workflow around the agent, and only 21% of firms have done it. Every use case ships with a redesigned SOP, and NTI reform - pre-approved patterns for reused agents, fewer and bigger use cases - takes the cycle from 145 days towards under 60. Technology is the "20": one platform path from FY26 with an eight-week release cadence, which is the pace JPMorgan runs for its LLM Suite, and token metering from FY27. Measured by agents reused across BUs (today zero) and use cases in production (today 15 of 37). Risk: Gartner expected 30% of gen-AI projects to be abandoned after proof of concept, and McKinsey finds senior oversight of AI governance is the factor most tied to impact. So a risk partner sits in every pod, the RCSA is updated for agents - the next slide - and a named executive owns AI governance. The bottom bar phases the four lenses across Assist, Orchestrate and Autonomize. References [1]-[7] are on the slide.